**SHORT FORM of Contract**

**GENER AL CONDITIONS**

First Edition 1999

ISBN 2-88432-024-5

FEDERATION INTERNATIONALE DES INGENIEURS-CONSEILS INTERNATIONAL FEDERATION OF CONSULTING ENGINEERS INTERNATIONALE VEREINI GUNG BERATENDER INGENIEURE FEDERACION INTERNACIONAL DE INGENIEROS CONSULTORES

**FIDIC**

**CONTENTS**

**General Conditions**

**GENERAL PROVISIONS** ........................ .. ... . .... **1**

**1 . 1** Definitions

The Contract

Persons

Dates, Times and Periods Money and Payments Other Definitions

**1** .2 Interpretation

1 .3 Priority of Documents

1.4 Law

1 .5 Communications

1.6 Statutory Obligations

**2 THE EMPLOYER** ................... .. .......... ...... .. . **2**

2.1 Provision of Site

2.2 Permits and Licences

2.3 Employer's Instructions

2.4 Approvals

**3 EMPLOYER'S REPRESENTATIVES** ........... .... ........... **3**

3.1 Authorised Person

3.2 Employer's Representative

**4 THE CONTRACTOR ..................................... . 3**

General Obligations

Contractor's Representative

**5 DESIGN BY CONTRACTOR** .................. ...... ....... . 3

5.1 Contractor's Design

5.2 Responsibility for Design

**6 EMPLOYER'S LIABILITIES** ................................ 4

6.1 Employer's Liabilities

7 **TIME FOR COMPLETION** ................................. 5

7.1 Execution of the Works

7.2 Programme

7.3 Extension of Time

7.4 Late Completion

**8 TAKING-OVER** . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . **5**

8.1 Completion

8.2 Taking-Over Notice

**9 REMEDYING DEFFECTS** ............. .... ................. **5**

9.1 Remedying Defects

9.2 Uncovering and Testing

**10 VARIATIONS AND CLAIMS** .......... .... ........ .. ........ **6**

10.1 Right to Vary

10.2 Valuation of Variations

10.3 Early Warning

10.4 Right to Claim

10.5 Variation and Claim Procedure

**11 CONTRACT PRICE AND PAYMENT** .......................... **7**

11.1 Valuation of the Works

11.2 Monthly Statements

11 .3 Interim Payments

11 .4 Payment of First Half of Retention

11.5 Payment of Second Half of Retention

11. 6 Final Payment

11 .7 Currency

11 .8 Delayed Payment


**12 DEFAULT** .............................................. 8

12.1 Default by Contractor

12.2 Default by Employer

12.3 Insolvency

12.4 Payment upon Termination



**RISK AND RESPONSIBILITY** ........................... . ... **9**

Contractor ' s Care of the Works

Force Majeure

**b**

14.1 Extent of Cover

14.2 Arrangements

14.3 Failure to Insure

**1*G* RESOLUTION OF DISPUTES** .............................. **10**

15.1 Adjudication

15.2 Notice of Dissatisfaction

15.3 Arbitration

**INDEX ....................................................... 11**

**General Conditions**

**1 - General Provisions**

**1.1**

**Definitions** In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

**The Contract** 1.1.1 **"Contract"** means the Agreement and the other documents listed in the

Appendix.

1.1.2 **"Specification"** means the document as listed in the Appendix, including Employer's requirements in respect of design to be carried out by the Contractor, if any, and any Variation to such document.

1.1.3 **"Drawings"** means the Employer ' s drawings of the Works as listed in the

Appendix, and any Variation to such drawings.

**Persons** 1.1.4 **" Employer"** means the person named in the Agreement and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

1.1.5 **"Contractor"** means the person named in the Agreement and the legal successors in title to this person, but not (except with the consent of the Employer) any assignee.

1.1.6 **"Party"** means either the Employer or the Contractor.

**Dates, Times and**

**Periods**

1 .1.7 **"Commencement Date"** means the date 14 days after the date the

Agreement comes into effect or any other date agreed between the Parties.

1.1.8 **"day"** means a calendar day.

1.1.9 **'Time for Completion"** means the time for completing the Works as stated in the Appendix (or as extended under Sub-Clause 7.3), calculated from the


Commencement Date.

**Money and Payments** 1.1.10 **"Cost"** means all expenditure properly incurred (or to be incurred ) by the Contractor, whether on or off the Site, including overheads and similar charges, but does not include profit.

**Other Definitions** 1.1.11 **"Contractor's Equipment"** means all apparatus, machinery, vehicles, facilities and other things required for the execution of the Works but does not include Materials or Plant.

1.1.12 **"Country"** means the country in which the Site is located.

**"Employer's Liabilities"** means those matters listed in Sub-Clause 6.1.



**" Force Majeure"** means an exceptional event or circumstance: which is beyond a Party's control; which such Party could not reasonably have

such Party could not reasonably have avoided or overcome; and, which is not substantially attributable to the other Party.

1.1.15 **"Materials"** means things of all kinds (other than Plant) intended to form or forming part of the permanent work.

1 .1.16 **"Plant"** means the machinery and apparatus intended to form or forming part of the permanent work.

1.1.17 **"Site"** means the places provided by the Employer where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18 **"Variation"** means a change to the Specification and /or Drawings (if any)

which is instructed by the Employer under Sub-Clause 10.1.

1.1 .19 **"Works"** means all the work and design (if any) to be performed by the

Contractor including temporary work and any Variation

**1.2**

**Interpretation** Words importing persons or parties shall include firms and organisations. Words importing singular or one gender shall include plural or the other gender where the context requires.

**1.3**

**Priority of Documents** The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the Employer shall issue any necessary instructions to the Contractor, and the priority of the documents shall be in accordance with the order as listed in the Appendix.

**1.4**

**Law** The law of the Contract is stated in the Appendix.

**1.5**

**Communications** Wherever provision is made for the giving or issue of any notice, instruction, or other communication by any person, unless otherwise specified such communication shall be written in the language stated in the Appendix and shall not be unreasonably withheld or delayed.

**1.6**


**Statutory Obligations** The Contractor shall comply with the laws of the countries where activities are performed. The Contractor shall give all notices and pay all fees and other charges in

respect of the Works.

**2.1**



**Provi sion of Site**



**2.2**

The Employer shall provide the Site and right of access thereto at the times stated in

--=----=-o--o · e Appendix.

**;;c:=.<**

?

**Permits and Li** e mployer shall, if requested by the Contractor, assist him in applying for permits,

**N:o';**

e ces or approvals which are required for the Works.

**2** © *J::'tDI C* 9;cf>

Short Form of Contract

Employer's Instructions

the Works including the suspension of all or part of the Works.

2.4

Approvals No approval or consent or absence of comment by the Employer or the Employer's representative shall affect the Contractor's obligations.



**E**

3.1

Authorised Person One of the Employer's personnel shall have authority to act for him. This authorised person shall be as stated in the Appendix, or as otherwise notified by the Employer to the Contractor.


3.2

Employer's

Representative

The Employer may also appoint a firm or individual to carry out certain duties. The appointee may be named in the Appendix, or notified by the Employer to the Contractor from time to time. The Employer shall notify the Contractor of the delegated duties and authority of this Employer's representative.

**Th ntractor**



4.1

General Obligations The Contractor shall carry out the Works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor's Equipment which may be required. All Materials and Plant on Site shall be deemed to be the property of the Employer.

4.2

Contractor's

Representative

The Contractor shall submit to the Employer for consent the name and particulars of the person authorised to receive instructions on behalf of the Contractor.

4.3

Subcontracting The Contractor shall not subcontract the whole of the Works. The Contractor shall not subcontract any part of the Works without the consent of the Employer.

4.4

Performance Security If stated i



The Contractor shall not

The Contractor shall not subcontract the whole of the Works. The Contractor shall not subcontract any part of the Works without the consent of the Employer.

If stated in the Appendix, the Contractor shall deliver to the Employer within 14 days of the Commencement Date a performance security in a form and from a third party approved by the Employer.

5.1

Contractor's Design

The Contractor shall carry out design to the extent specified, as referred to in the Appendix. The Contractor shall promptly submit to the Employer all designs prepared by him. Within 14 days of receipt the Employer shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons.

Design that has been rejected shall be promptly amended and resubmitted. The

Contractor shall resubmit all designs commented on taking these comments into account as necessary.

**5.2**

**Responsibility for**

**Design**

The Contractor shall remain responsible fol- his tendemd design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Employer shall be responsible for the Specification and

Drawings.



**E er's Liabilities**



**6.1**

**Employer's Liabilities** In this Contract, Employer's Liabilities mean :

|  |  |  |
| --- | --- | --- |
|  | a) | war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country, |
| b)  c) | rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country,  riot, commotion or disorder by persons other than the Contractor's personnel |
| d) | and other employees, affecting the Site and/or the Works,  ionising radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor may be responsible for the use of any radio-active |
| e) | material,  pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds,  use or occupation by the Employer of any part of the Works, except as may be |
| g)  h) | specified in the Contract,  design of any part of the Works by the Employer's personnel or by others for whom the Employer is responsible, and  any operation of the forces of nature affecting the Site and/or the Works, which was unforeseeable or against which an experienced contractor could not reasonably have been expected to take precautions. |
| i)  j) | Force Majeure,  a suspension under Sub-Clause 2.3 unless it is attributable to the Contractor's |
| k) | failure,  any failure of the Employer, |
| I) | physical obstructions or physical conditions other than climatic conditions, encountered on the Site during the performance of the Works, which obstructions or conditions were not reasonably foreseeable by an experienced contractor and which the Contractor immediately notified to the Employer, |
| m)  n) | any delay or disruption caused by any Variation,  any change to the law of the Contract after the date of the Contractor's offer |
|  |  | as stated in the Agreement,  losses arising out of the Employer's right to have the permanent work executed on, over, under, in or through any land, and to occupy this land for the permanent work, and  damage which is an unavoidable result of the Contractor's obligations to execute the Works and to remedy any defects. |
| **4** |  | Sl1ort Form of Contract |

**Ti for Completion**



**7.1**

**Execution of the Works** The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works within the Time for Completion.

**7.2**

**Programme** Within the time stated in the Appendix, the Contractor shall submit to the Employer a programme for the Works in the form stated in the Appendix.

**7.3**

**Extension of Time** Subject to Sub-Clause 10.3, the Contractor shall be entitled to an extension to the Time for Completion if he is or will be delayed by any of the Employer' s Liabilities.

On receipt of an application from the Contractor, the Employer shall consider all supporting details provided by the Contractor and shall extend the Time for Completion as appropriate.

**7.4**

**Late Completion** If the Contractor fails to complete the Works within the Time for Completion, the Contractor's only liability to the Employer for such failure shall be to pay the amount stated in the Appendix for each day for which he fails to complete the Works.

**Ta-Over**



**8.1**

**Completion** The Contractor may notify the Employer when he considers that the Works are complete.

**8.2**

**Taking-Over Notice** The Employer shall notify the Contractor when he considers that the Contractor has completed the Works stating the date accordingly. Alternatively, the Employer may notify the Contractor that the Works, although not fully complete, are ready for taking over, stating the date accordingly.

The Employer shall take over the Works upon the i ssue of this notice. The Contractor shall promptly complete any outstanding work and, subject to Clause 9, clear the Site.

9.

**Remedying Defects**



**9.1**

mployer may at any time prior to the expiry of the period stated in the Appendix,

**,..,E;"f.'i.\** the Contractor of any defects or outstanding work. The Contractor shall remedy cost to the Employer any defects due to the Contractor's design, Materials,

or workmanship not being in accordance with the Contract.

General Conditions **5**

The cost of remedying defects attributable to any other cause shall be valued as a Variation. Failure to remedy any defects or complete outstanding work within a reasonable time of the Employer's notice shall entitle the Employer to carry out all necessary work at the Contractor's cost.

**9.2**

**Uncovering and Testing** The Employer may give in:>truction a:> to the uncovering and/or te:>ting of any work.

Unless as a result of any uncovering and/or testing it is established that the Contractor's design, Materials, Plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.



**and Claims**

**10.1**

**Right to Vary**

The Employer may instruct Variations.

**1 0.2**

**Valuation of Variations** Variations shall be valued as follows:

a) at a lump sum price agreed between the Parties, or b) where appropriate, at rates in the Contract, or

c) in the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which

d) at appropriate new rates, as may be agreed or which the Employer considers appropriate, or

e) if the Employer so instructs, at daywork rates set out in the Appendix for which the Contractor shall keep records of hours of labour and Contractor's Equipment, and of Materials used.

**10.3**

**Early Warning** A Party shall notify the other as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. The Contractor shall take all reasonable steps to minimise these effects.

The Contractor's entitlement to extension to the Time for Completion or additional payment shall be limited to the time and payment which would have been due if he had given prompt notice and had taken all reasonable steps.

**10.4**

**Right to Claim** If the Contractor incurs Cost as a result of any of the Employer's Liabilities, the Contractor shall be entitled to the amount of such Cost. If as a result of any of the Employer's Liabilities, it is necessary to change the Works, this shall be dealt with as

a Variation.

**1 0.5**

**Variation and Claim**

**Procedure**

The Contractor shall submit to the Employer an itemised make-up of the value of Variations and claims within 28 days of the instruction or of the event giving rise to the claim. The Employer shall check and if possible agree the value. In the absence of

*Do* reement, the Employer shall determine the value.



**:::::::::10;**

**6** Sl1ort Form of Contract

**Contract Price and Payment**

**11.1**

**Valuation of the Works** The Works shall be valued as provided for in the Appendix, subject to Clause 10.

**11.2**

**Monthly Statements** The Contractor shall be entitled to be paid at monthly intervals:

a) the value of the Works executed,

b) the percentage stated in the Appendix of the value of Materials and Plant delivered to the Site at a reasonable time,

subject to any additions or deductions which may be due.

The Contractor shall submit each month to the Employer a statement showing the amounts to which he considers himself entitled.

**11.3**

**Interim Payments** Within 28 days of delivery of each statement, the Employer shall pay to the Contractor the amount shown in the Contractor ' s statement less retention at the rate stated in the Appendix, and less any amount for which the Employer has specified his reasons for disagreement. The Employer shall not be bound by any sum previously considered by him to be due to the Contractor.

The Employer may withhold interim payments until he receives the performance security under Sub-Clause 4.4 (if any).

**11.4**

**Payment of First Half of**

**Retention**

One half of the retention shall be paid by the Employer to the Contractor within 14 days after issuing the notice under Sub-Clause 8.2.

**11.5**

**Payment of Second Half of Retention**

The remainder of the retention shall be paid by the Employer to the Contractor within


14 days after either the expiry of the period stated in the Appendix, or the remedying of notified defects or the completion of outstanding work, all as referred to in Sub­ Clause 9.1, whichever is the later.

**11.6**

**Final Payment** Within 42 days of the latest of the events listed in Sub-Clause 11.5 above, the Contractor shall submit a final account to the Employer together with any documentation reasonably required to enable the Employer to ascertain the final contract value.

Within 28 days after the submission of this final account, the Employer shall pay to the Contractor any amount due. If the Employer disagrees with any part of the Contractor's final account, he shall specify his reasons for disagreement when making payment.

**11.7**



**Currency**

ontractor shall be entitled to interest at the rate stated in the Appendix for each he Employer fails to pay beyond the prescribed payment period.

General Conditions **7**



**12.1**

**Default by Contractor** If the Contractor abandons the Works, refuses or fails to comply with a valid instruction of the C::mploye1· or fails to pmceed expeditiously and without delay, m is, despite a written complaint, in breach of the Contract, the Employer may give notice referring to this Sub-Clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within 14 days after the Contractor's receipt of the Employer's notice, the Employer may by a second notice given within a further 21 days, terminate the Contract. The Contractor shall then demobilise from the Site leaving behind Materials and Plant and any Contractor's Equipment which the Employer instructs in the second notice is to be used until the completion of the Works.

**12.2**

**Default by Employer** If the Employer fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within 7 days after the Employer's receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within 28 days after the Employer's receipt of the

Contractor's notice, the Contractor may by a second notice given within a further

21 days, terminate the Contract. The Contractor shall then demobilise from the

Site.

**12.3**

**Insolvency** If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The Contractor shall then demobilise from the Site leaving behind, in the case of the Contractor's insolvency, any Contractor ' s Equipment which the Employer instructs in the notice is to be used until the

completion of the Works.

**12.4**

**Payment upon**

**Termination**

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:


a) any sums to which the Contractor is entitled under Sub-Clause 10.4, b) any sums to which the Employer is entitled,

c) if the Employer has terminated under Sub-Clause 12.1 or 12.3, the Employer shall be entitled to a sum equivalent to 20% of the value of those parts of the Works not executed at the date of the termination,

d) if the Contractor has terminated under Sub-Clause 12.2 or 12.3, the Contractor shall be entitled to the Cost of his suspension and demobilisation together with a sum equivalent to 10% of the value of those parts of the Works not executed

at the date of termination.

due shall be paid or repaid within 28 days of the notice of



**8** Short Form of Contract

**esponsibility**



**13.1**

**Contractor's Care of the** The Contractor shall take full responsibility for the care of the Works from the

**Works** Commencement Date until the date of the Employer's notice under Sub-Clause 8.2.

Responsibility shall then pass to the Employer. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform with the Contract.

Unless the loss or damage happens as a result of an Employer's Liability, the Contractor shall indemnify the Employer, the Employer's contractors, agents and employees against all loss or damage happening to the Works and against all claims or expense arising out of the Works caused by a breach of the Contract, by negligence or by other default of the Contractor, his agents or employees.

**13.2**

**Force Majeure** If a Party is or will be prevented from performing any of its obligations by Force Majeure, the Party affected shall notify the other Party immediately. If necessary, the Contractor shall suspend the execution of the Works and, to the extent agreed with the Employer, demobilise the Contractor ' s Equipment.

If the event continues for a period of 84 days, either Party may then give notice of termination which shall take effect 28 days after the giving of the notice.

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

a) any sums to which the Contractor is entitled under Sub-Clause 10.4, b) the Cost of his suspension and demobilisation,

c) any sums to which the Employer is entitled.

The net balance due shall be paid or repaid within 28 days of the notice of termination.



**14.1**

**Extent of Cover** The Contractor shall, prior to commencing the Works, effect and thereafter maintain insurances in the joint names of the Parties:

a) for loss and damage to the Works, Materials, Plant and the Contractor ' s

Equipment,

b) for liability of both Parties for loss, damage, death or injury to third parties or their property arising out of the Contractor ' s performance of the Contract, including the Contractor ' s liability for damage to the Employer's property other than the Works, and



for liability of both Parties and of any Employer's representative for death or injury to the Contractor's personnel except to the extent that liability arises from the negligence of the Employer, any Employer's representative or their employees.

General Conditions **9**

**14.2**

**Arrangements**

All insurances shall conform with any requirements detailed in the Appendix. The policies shall be issued by insurers and in terms approved by the Employer. The Contractor shall provide the Employer with evidence that any required policy is in force and that the premiums have been paid.

All payments received from insurers relating to loss or damage to the Works shall be lel ld joilltly by tile Parties and used for tile repair of tile loss or damage or as compensation for loss or damage that is not to be repaired.

**14.3**

**Failure to Insure** If the Contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clauses, or fails to provide satisfactory evidence, policies or receipts, the Employer may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the Contractor.



**of Disputes**

**15.1**

**Adjudication** Unless settled amicably, any dispute or difference which arises between the Contractor and the Employer out of or in connection with the Contract, including any valuation or other decision of the Employer, shall be referred by either Party to adjudication in accordance with the attached Rules for Adjudication ("the Rules"). The adjudicator shall be any person agreed by the Parties. In the event of disagreement, the adjudicator shall be appointed in accordance with the Rules.


**15.2**

**Notice of Dissatisfaction** If a Party is dissatisfied with the decision of the adjudicator or if no decision is given within the time set out in the Rules, the Party may give notice of dissatisfaction referring to this Sub-Clause within 28 days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the adjudicator is revised by an arbitrator.

**15.3**

**Arbitration** A dispute which has been the subject of a notice of dissatisfaction shall be finally settled by a single arbitrator under the rules specified in the Appendix. In the absence of agreement, the arbitrator shall be designated by the appointing authority specified in the Appendix. Any hearing shall be held at the place specified in the Appendix and in the language referred to in Sub-Clause 1.5.

**10** Sl1ort Form of Contract



**INDEX OF SUB-CLAUSES**

|  |  |  |  |
| --- | --- | --- | --- |
|  | Adjudication | Sub-Clause  15.1 | Page  10 |
| Approvals | 2.4 | 3 |
| Arbitration | 15.3 | 10 |
| Arrangements, Insurance | 14.2 | 10 |
| Authorised person | 3.1 | 3 |
| Communications | 1.5 | 2 |
| Completion | 8.1 | 5 |
| Contractor's Care of the Works | 13.1 | 9 |
| Contractor's Design | 5.1 | 3 |
| Contractor's Representative | 4.2 | 3 |
| Currency | 11.7 | 7 |
| Default by Contractor | 12.1 | 8 |
| Default by Employer | 12.2 | 8 |
| Definitions | 1. 1 |  |
| Delayed Payment | 11.8 | 7 |
| Early Warning, Claims | 10.3 | 6 |
| Employer's Instructions | 2.3 | 3 |
| Employer's Representative | 3.2 | 3 |
| Employer' s Liabilities | 6.1 | 4 |
| Execution of the Works | 7.1 | 5 |
| Extension of Time | 7.3 | 5 |
| Extent of Cover, Insurance | 14.1 | 9 |
| Failure to Insure | 14.3 | 10 |
| Final Payment | 11.6 | 7 |
| Force Majeure | 13. 2 | 9 |
| General Obligations, Contractor | 4.1 | 3 |
| Insolvency | 12.3 | 8 |
| Interim Payments | 11.3 | 7 |
| Interpretation | 1.2 | 2 |
| Late Completion | 7.4 | 5 |
| Law | 1.4 | 2 |
| Monthly Statements | 11. 2 | 7 |
|  |  | 15. 2 | 10 |
|  |  | 12.4 | 8 |
|  |  | 4.4 | 3 |
|  |  | 2.2 | 2 |
|  |  | 1.3 | 2 |
| General Conditions |  |  | 11 |

|  |  |  |
| --- | --- | --- |
| Programme | 7.2 | 5 |
| Provision of Site | 2.1 | 2 |
| Remedying Defects | 9.1 | 5 |
| Responsibility for Design | 5.2 | 4 |
| Retention, First Half | 11.4 | 7 |
| Retention, Second Half | 11.G | 7 |
| Right to Claim | 10.4 | 6 |
| Right to Vary | 10.1 | 6 |
| Statutory Obligations | 1. 6 | 2 |
| Subcontracting | 4.3 | 3 |
| Taking-Over Notice | 8.2 | 5 |
| Uncovering and Testing | 9.2 | 6 |
| Valuation of the Works | 11.1 | 7 |
| Valuation of Variations | 10.2 | 6 |
| Variation and Claim Procedure | 10.5 | 6 |

12 Sl1ort Form of Contract

